## Sheet1
Who? | Task | Notes | Date | Time spent | Simon
Simon | Setup project infrastructure | Created git and dropbox folders. Created presentation and log template. | 14.3 | 2h | Laurent
Simon | Started initial plan | Added project context | 14.3 | 1h
Simon | Initial plan | Added goals and objectives to initial plan | 17.3 | 1h
Simon | Setup project infrastructure | Created code folder and structur. Added small demo script. | 17.3 | 1h
Laurent | Introduction to video processing with Matlab | Started to learn how to process videos with Matlab | 17.3 | 1h
Laurent | Initial plan | Added: project organization, constraints & elem of risks and deliverables parts | 19.3 | 2h
Simon | Initial plan | Added methodology | 20.3 | 1h