## work_log.csv
Who? | Task | Notes | Date | Time spent | Simon
Simon | Setup project infrastructure | Created git and dropbox folders. Created presentation and log template. | 2016-03-14 | 2h | Laurent
Simon | Started initial plan | Added project context | 2016-03-14 | 1h
Simon | Initial plan | Added goals and objectives to initial plan | 2016-03-17 | 1h
Simon | Setup project infrastructure | Created code folder and structur. Added small demo script. | 2016-03-17 | 1h
Laurent | Introduction to video processing with Matlab | Started to learn how to process videos with Matlab | 2016-03-17 | 1h
Laurent | Initial plan | Added: project organization, constraints & elem of risks and deliverables parts | 2016-03-19 | 2h
Simon | Initial plan | Added methodology | 2016-03-20 | 1h
Simon | Initial plan | Added efforts and schedule | 2016-03-20 | 1h
Simon | Sprint planning | Setup Taiga and planning for Sprint 1 | 2016-03-20 | 1h
Simon | Initial plan | Worked on slides | 2016-03-20 | 1h
Laurent | Initial plan | Worked on slides | 2016-03-21 | 1h
Laurent | Introduction to video processing with Matlab | Learning to use Matlab for video processing | 2016-03-21 | 1h
Laurent | Initial plan | Worked on slides | 2016-03-21 | 1h
Simon | Development | Implement function that extracts video-data | 2016-03-21 | 1h
Simon | Development | Implement loading of all videos contained in a folder and subfolders | 2016-03-21 | 1h
Simon | Development | Started implementing the generation of synthetic test data | 2016-03-22 | 2h
Laurent | #7 Taiga | Function that save extracted data for later reuse | 2016-03-22 | 1h
Simon | Development | Finished function that generates synthetic data | 2016-03-25 | 1h
Simon | Development | Refactored and finalised extraction and storing of video data | 2016-03-25 | 1h
Simon | Development | Implemented function which adds noise to synthetic data | 2016-03-25 | 1h
Simon | Development | Initial implementation of frequency analysis using FFT (ROI=Pixels only) | 2016-03-26 | 2h
Simon | Refactoring + Testing | Code clean up and refactoring. Added test-script for FFT. | 2016-03-27 | 1h
Simon | Development | Added support for different ROI-sizes | 2016-03-28 | 1h
Simon | Initial plan | Finalizing initial plan: Apply feedback, add SotA and sprint plans. | 2016-03-29 | 1h
Simon | Development | Generate activity image based on fft-power | 2016-03-31 | 2h
Simon | Development | Storing of activity image + batch analysis of folder | 2016-04-04 | 2h
Simon | Development | Improving output, bug fixing and support for parallel comutations | 2016-04-05 | 2h
Laurent | Reviewing and testing | Reviewed and tested Simon's code | 2016-04-10 | 4h
Laurent | Reviewing and testing | Reviewed and tested Simon's code | 2016-04-11 | 2h
Laurent | Sprint planning | Meeting with Laurent and Patrice + plannign | 2016-04-11 | 1h
Simon | Sprint planning | Meeting with Laurent and Patrice + plannign | 2016-04-11 | 1h
Laurent | Development | Researched about max entropy method and started implementation | 2016-04-14 | 4h
Laurent | Development | Implemented max entropy method for activity and spectral analysis | 2016-04-17 | 3h
Laurent | Development | Fixed max entropy method | 2016-04-18 | 1h
Simon | Reviewing and testing | Code-reviews | 2016-04-17 | 1h
Simon | Refactoring | Refactored plotting | 2016-04-18 | 2h
Simon | Development | Implemented activity mask and adjusted plotting | 2016-04-18 | 1h
Laurent | Reviewing and testing | Code reviews | 2016-04-19 | 1h
Laurent | Development | Implentation of activity analysis with Wavelet transform | 2016-05-01 | 5h
Simon | Development | Implement frequency image | 2016-05-01 | 1h
Simon | Development | Adjust down-sampling ro handle arbitrary ROI-size | 2016-05-01 | 1h
Laurent | Reviewing and testing | Reviewed, tested, and tried code on videos from Patrice | 2016-05-05 | 2h
Simon | Development | Saving of results as .mat files | 2016-03-05 | 1h
Simon | Development | GUI | 2016-05-06 | 4h
Simon | Presentations | Worked on Midpoint slides | 2016-05-07 | 2h
Laurent | Reviewing and testing | Tested GUI and reviewed code | 2016-05-07 | 2h
Simon | Development | Added missing features to GUI | 2016-05-08 | 1h
Simon | Development | Added phase extraction to FFT | 2016-05-08 | 1h
Laurent | Reviewing and testing | Tested new features and reviewed code | 2016-05-09 | 1h
Laurent | Development | Error handling for the GUI + testing | 2016-05-09 | 3h
Laurent | Presentations | Worked on Midpoint slides | 2016-05-09 | 1h
Simon | Development | Frequency analysis using WT | 2016-05-09 | 2h
Laurent | Comparison of results | Did a small comparison of our results vs Patrice's results | 2016-05-10 | 1h
Laurent | Development | Updated slides and added WT to demo | 2016-05-10 | 3h
Simon | Development | Improved GUI (faster loading) and added Phase image and histograms | 2016-05-18 | 3h
Simon | Testing and Bug fixing | Phase extraction and selection of ROI in GUI fixed and tested | 2016-05-20 | 3h
Laurent | Development | Modified WT + batchAnalyseFolder -> add parameter to choose wavelet | 2016-05-24 | 1h
Laurent | Development | Finished adding WT to demo | 2016-05-25 | 1h
Simon | Testing and Bug fixing | Code review | 2016-05-25 | 1h
Simon | Refactoring | Refactored batchAnalFolder... | 2016-05-25 | 1h
Simon | Development | Added WT to GUI | 2016-05-25 | 1h
Laurent | Reviewing and testing | Tested new code | 2016-05-29 | 1h
Laurent | Final report + code reviewing | Created final report, and added relevant part from initial plan + code review | 2016-05-30 | 2h
Simon | Bug-fixing and testing | Fixed bugs in GUI and phase computation | 2016-05-31 | 2h
Simon | Development | Started implementation of function that estimates probable beating pattern | 2016-05-31 | 2h
Simon | Development | Improved probable shape estimation using function fitting via smoothing splines | 2016-06-08 | 2h
Simon | Final report | Added function headers for documentation | 2016-06-10 | 2h
Simon | Development | Improved probable shape estimation and added it to results | 2016-06-18 | 1h
Laurent | Speed tests | Wrote speed tests (and did not work because of bugs) | 2016-06-19 | 2h
Laurent | Speed tests | Modified speed tests | 2016-06-20 | 2h
Laurent | Final report | Added results to final report | 2016-06-20 | 1h
Laurent | Final report | Different wavelets + comparison methods + slides + report | 2016-06-21 | 5h
Simon | Final presentation | Worked on slides | 2016-06-21 | 2h
Simon | Bug fixing | Fixed bug in the Wavelet transform not allow all types of wavelets | 2016-06-21 | 2h
Simon | Final report | Wrote section on realisation | 2016-06-21 | 1h
Simon | Final report | Adjusted and corrected evaluation section | 2016-06-21 | 1h
Simon | Final report | Wrote recomendations, limitations and future work. | 2016-06-21 | 1h
Simon | Documentation and README | Updated the README for the tool | 2016-06-21 | 1h