## Sheet1
Who? | Task | Notes | Date | Time spent | Simon
Simon | Setup project infrastructure | Created git and dropbox folders. Created presentation and log template. | 2016-03-14 | 2h | Laurent
Simon | Started initial plan | Added project context | 2016-03-14 | 1h
Simon | Initial plan | Added goals and objectives to initial plan | 2016-03-17 | 1h
Simon | Setup project infrastructure | Created code folder and structur. Added small demo script. | 2016-03-17 | 1h
Laurent | Introduction to video processing with Matlab | Started to learn how to process videos with Matlab | 2016-03-17 | 1h
Laurent | Initial plan | Added: project organization, constraints & elem of risks and deliverables parts | 2016-03-19 | 2h
Simon | Initial plan | Added methodology | 2016-03-20 | 1h
Simon | Initial plan | Added efforts and schedule | 2016-03-20 | 1h
Simon | Sprint planning | Setup Taiga and planning for Sprint 1 | 2016-03-20 | 1h
Simon | Initial plan | Worked on slides | 2016-03-20 | 1h
Laurent | Initial plan | Worked on slides | 2016-03-21 | 1h
Laurent | Introduction to video processing with Matlab | Learning to use Matlab for video processing | 2016-03-21 | 1h